## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
AD represents admin |  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
AD001 | View Overall and Detailed Workload of All TAs | As a system admin I want to view the total workload of all TAs with one click and check their specific assigned tasks by clicking on their names, without tedious searching So that I can quickly judge if the workload allocation among TAs is fair and avoid uneven workload distribution | High |  | 1. A workload summary card on the homepage displays the total number of TAs in the school, the average workload, and the number of TAs with excessive workload 2. The list shows each TA's name, total number of tasks, total working hours, and the names of TAs with excessive workload are highlighted in red 3. Clicking on a TA's name can expand task details, including task name, assigned MO, task time and completion status 4. Supports search by TA name and filter by task type (Module Support/Invigilation), with real-time refresh of results | 3 story points | Core mandatory function, integrated with the MO task allocation function | 2026-03-20 | 2026-03-26
AD002 | Add/Edit/Deactivate TA Accounts with Operation Records | As a system admin I want to create login accounts for new TAs, edit information such as phone numbers and majors for existing TAs, deactivate accounts for graduated/resigned TAs, and keep records of all these operations So that only valid TAs of the school can log in to the system, account information is updated in a timely manner, and accountability can be traced if problems occur | High |  | 1. Create an account: Enter the TA's name, student ID/staff ID and phone number, the system automatically generates an account, and the initial password can be set manually 2. Edit information: Modify the basic information of the TA's account directly, which takes effect immediately after saving, and the old information is archived automatically 3. Deactivate an account: After clicking the "Deactivate" button, the account cannot log in to the system immediately, and the button changes to "Deactivated" synchronously | 2 story points | Fundamental function for TAs to use the system, to be developed synchronously with Sprint 1 core functions | 2026-03-20 | 2026-03-26
AD003 | Check MOs' Task Posting Permissions with One-Click Approval/Rejection | As a system admin I want to view MOs' applications for task posting permissions in the background, conduct quick reviews with one-click approval or rejection, and write rejection reasons if needed So that only school-authorized MOs can post TA positions and prevent fake task postings by external personnel | Medium |  | 1. The system has a dedicated "MO Permission Review" page, with pending applications ranked first and highlighted in red as a reminder 2. The application card displays the MO's name, department, specific applied permissions and uploaded employment certification materials 3. Review operations: Click "Approve" and the MO will obtain the corresponding permissions immediately; click "Reject" to enter the reason, which can be viewed by the MO after logging in 4. After the review is completed, the application is automatically classified into the "Approved/Rejected" list, supporting filtering by name/review status | 2 story points | Dependent on the MO-side permission application function | 2026-03-27 | 2026-03-31
AD004 | Batch Import/Export TA Basic Information | As a system admin I want to batch import TA basic information via CSV files and export all TA information as CSV files with one click So that there is no need to create TA accounts one by one, improve work efficiency, and facilitate backing up TA data or submitting it to the school for filing | Medium |  | 1. Batch export: Export all TA information with one click, including account status and basic information, the file format meets the requirements of plain text 2. Export filter: Support filtering by account status (Active/Deactivated) and export only the TA information that meets the conditions | 1 story points | maybe "export"is more needed | 2026-03-27 | 2026-03-31
AD005 | View All System Operation Records with CSV Export Function | As a system admin I want to view all operations of TAs, MOs and other admins in the system, and export the filtered records as CSV files to the computer So that I can accurately trace who performed irregular operations (e.g., modifying tasks, deleting information) and when | Medium |  | 1. Operation records include: operator, account type (TA/MO/Admin), operation type, operation time, operation content and operation result 2. Support multi-condition combined filtering: filter by account type, operation type and time range, with one-click refresh of results 3. Export function: Click "Export CSV" and the file is downloaded directly to the computer, the format meets the project's plain text requirements | 2 story points | Necessary function for system security, non-core but mandatory, to be developed and completed in Sprint 3 | 2026-04-01 | 2026-04-06
AD006 | Quickly Freeze Abnormal TA/MO Accounts | As a system admin I want to freeze the accounts of TAs/MOs with abnormal operations with one click, such as multiple login failures, posting fake positions, malicious applications, etc. So that stop irregular operations in time, prevent system data from being tampered with, and ensure the order of system use and data security | low |  | 1. The system has a dedicated "Abnormal Accounts" list, displaying account name, account type, abnormal operation type and abnormal occurrence time 2. One-click freeze: After clicking the "Freeze" button, the account cannot log in and perform any system operations immediately | 2 story points | Supplementary function of account management, ensure system security, handle various account abnormal situations quickly | 2026-04-07 | 2026-04-12
AD007 | Check Unfilled TA Positions and Send Reminder to MOs | As a system admin I want to view all unfilled TA positions in the system, select the corresponding MOs and send one-click reminders for position supplementary recruitment So that urge MOs to supplement or adjust position requirements in time to ensure the smooth development of the school's teaching support work | low |  | 1. The system has an "Unfilled Positions" list, displaying position name, posting MO, required number of TAs, applied number of TAs and position posting time 2. Positions that have been posted for more than 7 days and are still unfilled are highlighted in red in the list to remind administrators to focus on them 3. One-click reminder: You can check the MOs corresponding to multiple unfilled positions and send in-system reminders with one click, including the position name and the number of vacancies in the content | 3 story points | Optimize the TA recruitment process, realize efficient linkage between administrators and MOs | 2026-04-12 | 2026-04-20
TA001 | Basic Personal Information | As a TA applicant, I want to create a basic profile in the system containing my personal information, so that the system can use it as base tags for automatic matching. | 1 | 1 | 1. Verify the system allows saving basic info like student ID and name. 2. Verify the system prompts and prevents saving when mandatory fields are empty. 3. Verify data is accurately written to a local text file. | 2 |  | 22/03/2026
TA002 | Undergraduate Course Grades Entry | As a TA applicant, I want to enter the core courses and grades I took during my undergraduate studies, so that the system can automatically identify if I meet the professional baseline during job matching. | 1 | 1 | 1. Verify multiple undergraduate course records can be dynamically added. 2. Verify the user can edit or delete records at any time. 3. Verify data is accurately saved to the local data document. | 3 |  | 22/03/2026
TA003 | CV Link | As a TA applicant, I want to submit an online viewable link to my standardized CV in the system, so that the Module Organiser can comprehensively evaluate my overall academic abilities. | 1 | 1 | 1. Verify the system provides a text box and validates the URL format. 2. Verify this field is mandatory. 3. Verify it is saved as plain text and displayed as a clickable hyperlink on the MO's side. | 1 |  | 22/03/2026
TA004 | Job Overview and Timetable | As a TA applicant, I want to browse all open positions for the current semester and see the start/end dates and full timetable, so that I can understand job opportunities and judge time conflicts. | 1 | 1 | 1. Verify only current semester jobs are displayed. 2. Verify clear display of MO, start/end dates, and timetable. 3. Verify data is read and rendered from plain text files. | 3 |  | 22/03/2026
TA005 | Application Status Dashboard | As a TA applicant, I want to view the real-time review status of all historical applications in a dashboard, so that I can keep track of the progress at any time. | 1 | 1 | 1. Verify historical applications are read and filtered by TA ID. 2. Verify clear display of module, time, and status. 3. Verify the frontend status updates synchronously with local data. | 3 |  | 22/03/2026
TA006 | One-Click Application & Data Association | As a TA applicant, I want to click a submit button to apply for the job with my profile and statement together, so that I can efficiently and standardly complete the entire application process. | 2 | 1 | 1. Verify the anti-duplicate submission mechanism. 2. Verify TA ID, Job ID, and statement are packaged into one application record. 3. Verify data is appended and written into a plain text file. | 3 |  | 22/03/2026
TA007 | Language Proficiency Details | As a TA applicant, I want to fill in my language exam scores, so that the system can use them as quantitative features for matching weight calculations. | 2 | 1 | 1. Verify the system provides a language type drop-down menu and score input. 2. Verify it is written to a local data document in CSV or JSON format. | 2 |  | 22/03/2026
TA008 | Supplementary Proof Materials Link | As a TA applicant, I want to submit a cloud drive link containing my additional proof documents in the system, so that I can provide factual support for specific statements in my CV. | 2 | 1 | 1. Verify the system provides a link input box and a short remark input box. 2. Verify this field is optional. 3. Verify data is successfully saved to local CSV/JSON. | 2 |  | 22/03/2026
TA009 | Filtered by Module Name | As a TA applicant, I want to search the current job list by entering a "module name", so that I can quickly locate courses relevant to my major. | 2 | 1 | 1. Verify a text search box is provided. 2. Verify support for fuzzy matching of module names. 3. Verify friendly prompts when there are no results. | 3 |  | 22/03/2026
TA010 | Filtered by Deadline | As a TA applicant, I want to sort by "application deadline" and distinguish between open and closed positions, so that I can prioritize applications for jobs that are about to close. | 2 | 1 | 1. Verify support for ascending sorting by deadline. 2. Verify graying out and disabling the apply button for closed positions. | 3 |  | 22/03/2026
TA011 | Filtered by MO Name | As a TA applicant, I want to filter jobs by the "MO's name", so that I can prioritize applying for courses taught by a supervisor I am familiar with. | 2 | 1 | 1. Verify an MO filtering drop-down or search is provided. 2. Verify results refresh in real-time to show only that MO's modules. | 2 |  | 22/03/2026
TA012 | Application Statement | As a TA applicant, I want to write a dedicated application statement when applying for a specific position, so that I can precisely explain to the MO why I am a match for this course. | 3 | 1 | 1. Verify a text box pops up for writing during application. 2. Verify there is a word limit and it is optional. 3. Verify support for special characters and correct writing to plain text files. | 2 |  | 22/03/2026
TA013 | Status Update Login Pop-up | As a TA applicant, I want the system to automatically pop up a notification upon login if there are status updates, so that I can be informed of the most important admission results immediately. | 3 | 1 | 1. Verify the system identifies "unread" status updates. 2. Verify a pop-up triggers upon logging into the homepage. 3. Verify it is marked as read after the pop-up is closed. | 3 |  | 22/03/2026