## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
AD represents admin |  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
AD001 | Mark TAs Who Have Taken 3 Courses and Restrict New Registrations | As a system admin I want to automatically mark TAs who have taken 3 courses and restrict them from registering for new course TA positions So that it complies with the rule "TAs can take at most 3 courses at the same time", no need to count workload, and directly control the registration limit | Must have | 1 | 1. The system automatically counts the number of course TA positions each TA currently holds, and marks "Reached Upper Limit" when the number = 3 2. When marked TAs register for new positions, the system pops up a prompt "Already holds 3 courses, cannot register for new positions" and blocks the registration operation 3. In the administrator page list, the names of TAs "Reached Upper Limit" are highlighted in red, with a note "Currently 3 courses" 4. Clicking on the TA's name allows viewing of specific course names, course MOs, and start times | 3 story points | focused on "3-course upper limit" control | 2026-03-20 | 2026-03-26
AD002 | Check Unfilled TA Positions and Send Reminder to MOs | As a system admin I want to view all unfilled TA positions in the system, select the corresponding MOs and send one-click reminders for position supplementary recruitment So that urge MOs to supplement or adjust position requirements in time to ensure the smooth development of the school's teaching support work | Must have | 1 | 1. The system has an "Unfilled Positions" list, displaying position name, posting MO, required number of TAs, applied number of TAs and position posting time 2. Positions that have been posted for more than 7 days and are still unfilled are highlighted in red in the list to remind administrators to focus on them 3. One-click reminder: You can check the MOs corresponding to multiple unfilled positions and send in-system reminders with one click, including the position name and the number of vacancies in the content | 3 story points | Optimize the TA recruitment process, realize efficient linkage between administrators and MOs (Priority raised to High according to teacher's suggestions, core linkage function) | 2026-04-12 | 2026-04-20
AD003 | Batch Import/Export TA Basic Information | As a system admin I want to batch import TA basic information via CSV files and export all TA information as CSV files with one click So that there is no need to create TA accounts one by one, improve work efficiency, and facilitate backing up TA data or submitting it to the school for filing | Should have | 1 | 1. Batch export: Export all TA information with one click, including account status and basic information, the file format meets the requirements of plain text 2. Export filter: Support filtering by account status (Active/Deactivated) and export only the TA information that meets the conditions | 1 story points | maybe "export"is more needed | 2026-03-27 | 2026-03-31
AD004 | View All System Operation Records with CSV Export Function | As a system admin I want to view all operations of TAs, MOs and other admins in the system, and export the filtered records as CSV files to the computer So that I can accurately trace who performed irregular operations (e.g., modifying tasks, deleting information) and when | Should have | 1 | 1. Operation records include: operator, account type (TA/MO/Admin), operation type, operation time, operation content and operation result 2. Support multi-condition combined filtering: filter by account type, operation type and time range, with one-click refresh of results 3. Export function: Click "Export CSV" and the file is downloaded directly to the computer, the format meets the project's plain text requirements | 2 story points | Necessary function for system security, non-core but mandatory, to be developed and completed in Sprint 3 | 2026-04-01 | 2026-04-06
AD005 | Quickly Freeze Abnormal TA/MO Accounts | As a system admin I want to freeze the accounts of TAs/MOs with abnormal operations with one click, such as multiple login failures, posting fake positions, malicious applications, etc. So that stop irregular operations in time, prevent system data from being tampered with, and ensure the order of system use and data security | Could have | 1 | 1. The system has a dedicated "Abnormal Accounts" list, displaying account name, account type, abnormal operation type and abnormal occurrence time 2. One-click freeze: After clicking the "Freeze" button, the account cannot log in and perform any system operations immediately | 2 story points | Supplementary function of account management, ensure system security, handle various account abnormal situations quickly | 2026-04-07 | 2026-04-12
TA001 | Comprehensive Personal Profile | As a TA applicant, I want to create a comprehensive profile containing my student ID, full name, email, phone number, research area and CET6 grade so that the system can use them as a basic knowledge for TA application. | Must have | 2 | 1. Verify the system allows saving basic info, dynamically adding information. 2. Verify the system prompts when mandatory fields are empty. 3. Verify data is accurately written to a local data document. | 5 story points | Record basic information of every TA and store them into system. | 2026-03-20 | 2026-03-26
TA002 | Application Status Dashboard | As a TA applicant, I want to view the real-time review status( "Approved as leader", "Approved as non-leader", "reject" or "interviewed") and feedback of all historical applications in a dashboard, so that I can keep track of the progress at any time. | Must have | 2 | 1. Verify historical applications are read and filtered by TA ID. 2. Verify clear display of module, time, and status and feedback. 3. Verify the frontend status updates synchronously with local data. 4. Verify there is a note that exists when the status of one application changed. | 3 story points | Forms a closed loop of business flow on the TA side. | 2026-03-20 | 2026-03-26
TA003 | Job Overview | As a TA applicant, I want to browse all the open jobs for the current semester and see the introduction of each job, so that I can decide which one to choose. | Must have | 2 | 1. Verify all the jobs are displayed. 2. Verify clear display of MO, course name, introduction, requirements and timetable (if provided by MO). | 3 story points | End dates of recruitment will be determined by MO; Timetable made optional as MOs cannot fully determine it before the semester. | 2026-03-20 | 2026-03-26
TA004 | Submit CV | As a TA applicant, I want to upload my CV in PDF format, so that the Module Organiser can comprehensively evaluate my overall academic abilities. | Must have | 2 | 1. Verify the system provides a file upload mechanism restricted to PDF format. 2. Verify this field is mandatory. 3. Verify the system saves the files locally for displaying to MOs. | 3 story points | Core strategy using internal file paths instead of external links. | 2026-03-20 | 2026-03-26
TA005 | TA Application Role Selection | As a TA applicant, I want to be able to select to apply for either the leader or non-leader role when applying for a course position, so that I can clearly understand my application intention and admission result. | Must have | 2 | 1. Verify that the TA can select either the "leader" or "non-leader" role when submitting a course application. 2. Verify that only three statuses are displayed in the application list: leader, non-leader, not hired. 3. Verify that the role selected during application (leader / non-leader) is correctly stored and displayed in the application record. 4. Verify that multiple TAs (including both leader and non-leader roles) can be admitted for a single course position simultaneously. | 2 story points | The same in the real world TA application. | 2026-03-27 | 2026-03-31
TA006 | Application Statement-Feedback Chat Box | As a TA applicant, I want to communicate with MD when apply for jobs, so that I can let MD have a better understanding of my overall abilities. | Should have | 2 | 1. Verify that the chat box for typing words works during the application process. 2. Verify that the chat box for typing words based on MD's feedback works at application status dashboard. 3. Verify that there is a word limit in the chat box. | 2 story points | Provide applicants with an additional channel for in-depth communication with instructors, helping the MO better understand the applicant’s motivation, strengths and fit for the role. | 2026-04-01 | 2026-04-07
TA007 | Search for Module Name | As a TA applicant, I want to search the current job list by entering a "module name", so that I can quickly locate courses relevant to my major. | Could have | 2 | 1. Verify a text search box is provided. 2. Verify support for fuzzy matching of module names. 3. Verify friendly prompts when there are no results. | 2 story points | Improves job search efficiency. | 2026-04-01 | 2026-04-07
TA008 | Filtered by MO Name | As a TA applicant, I want to filter jobs by the "MO's name", so that I can prioritize applying for courses taught by a supervisor I am familiar with. | Could have | 2 | 1. Verify an MO filtering drop-down or search is provided. 2. Verify results refresh in real-time to show only that MO's modules. | 2 story points | Fits the real-world job-seeking scenario of postgraduates. | 2026-04-01 | 2026-04-07
MO001 | Publish TA Recruitment Jobs | As a MO, I want to publish TA recruitment jobs with detailed information, so that eligible TA applicants can browse and apply for the relevant jobs. | Must have | 1 | 1. MO can fill in core job information (job title, skill requirements, weekly workload, application deadline); 2. Published jobs are automatically displayed in the "Available Jobs" section of the system; 3. Job information is automatically saved as a JSON file after submission; 4. Only the publishing MO can edit their own jobs, and administrators can view all MO-published jobs. 5.MO can restrict only TA with specific conditions to apply at the time of release | 3 story points | Naming rule for storage files: MO_JobID_PublishDate.json; | 2026-03-20 | 2026-03-26
MO002 | View Applicant List for Published Jobs | As a MO, I want to view a complete list of applicants for the jobs I published, so that I can quickly get an overview of all applicants for my jobs. | Must have | 1 | 1. After logging in, MO can only view applicants for their own published jobs, not for other MOs' jobs; 2. The list displays the following fields: Applicant ID, Name, Application Time, Application Status; 3. Clicking the applicant's name jumps to the CV detail page; 4. The list supports filtering by application status (Pending Review/Approved/Rejected). | 2 story points | Applicant skill tags extract core keywords from TA resumes; | 2026-03-20 | 2026-03-26
MO003 | Filter and Mark Applicant Status | As a MO, I want to mark applicants' status as "Approved"/"Rejected"/"Pending Interview" for the jobs I published, so that I can manage the recruitment review process and notify applicants of the results. | Must have | 1 | 1. MO can mark the status of each applicant individually, and the status is automatically synced to the applicant's system account; 2. After marking as "Approved"/"Rejected", the system automatically generates a status notification and saves it to the applicant's notification file; 3. Marking records are automatically saved with Marked By, Mark Time and Status for traceability; | 2 story points | Status marking data is stored in JSON format and associated with Job ID-Applicant ID; | 2026-03-20 | 2026-03-26
MO004 | Edit and Delete Published Jobs | As a MO, I want to edit the details of my published jobs and take down jobs that are no longer recruiting, so that I can update job information and stop invalid applications. | Should have | 1 | 1. MO can edit all job information before the application deadline, and the edited content is automatically updated in the system display; 2. MO can take down jobs at any time, and the taken-down jobs are hidden from the "Available Jobs" section and no longer accept new applications; 3. The applicant list of taken-down jobs can still be viewed and managed normally; 4. All edit/take-down operations are logged with Operator, Time and Operation Type; 5. Jobs are automatically marked as "Closed" after the deadline and cannot be edited or republished. | 3 story points | 1. Edit operations only modify the original job CSV file without generating new files; 2. Take-down status is stored in the JSON configuration file of job information; 3. Deadline automatic validation is triggered regularly by the system. | 2026-03-27 | 2026-03-31