## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
|  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
MO001 | Publish TA Recruitment Jobs | As a MO, I want to publish TA recruitment jobs with detailed information, so that eligible TA applicants can browse and apply for the relevant jobs. | Must have | 1 | 1. MO can fill in core job information (job title, skill requirements, weekly workload, application deadline); 2. Published jobs are automatically displayed in the "Available Jobs" section of the system; 3. Job information is automatically saved as a JSON file after submission; 4. Only the publishing MO can edit their own jobs, and administrators can view all MO-published jobs. 5.MO can restrict only TA with specific conditions to apply at the time of release | 3 story points | Naming rule for storage files: MO_JobID_PublishDate.json; | 2026-03-20 | 2026-03-26
MO002 | View Applicant List for Published Jobs | As a MO, I want to view a complete list of applicants for the jobs I published, so that I can quickly get an overview of all applicants for my jobs. | Must have | 1 | 1. After logging in, MO can only view applicants for their own published jobs, not for other MOs' jobs; 2. The list displays the following fields: Applicant ID, Name, Application Time, Application Status; 3. Clicking the applicant's name jumps to the CV detail page; 4. The list supports filtering by application status (Pending Review/Approved/Rejected). | 2 story points | Applicant skill tags extract core keywords from TA resumes; | 2026-03-20 | 2026-03-26
MO003 | Filter and Mark Applicant Status | As a MO, I want to mark applicants' status as "Approved"/"Rejected"/"Pending Interview" for the jobs I published, so that I can manage the recruitment review process and notify applicants of the results. | Must have | 1 | 1. MO can mark the status of each applicant individually, and the status is automatically synced to the applicant's system account; 2. After marking as "Approved"/"Rejected", the system automatically generates a status notification and saves it to the applicant's notification file; 3. Marking records are automatically saved with Marked By, Mark Time and Status for traceability; | 2 story points | Status marking data is stored in JSON format and associated with Job ID-Applicant ID; | 2026-03-20 | 2026-03-26
MO004 | Edit and Delete Published Jobs | As a MO, I want to edit the details of my published jobs and take down jobs that are no longer recruiting, so that I can update job information and stop invalid applications. | Should have | 1 | 1. MO can edit all job information before the application deadline, and the edited content is automatically updated in the system display; 2. MO can take down jobs at any time, and the taken-down jobs are hidden from the "Available Jobs" section and no longer accept new applications; 3. The applicant list of taken-down jobs can still be viewed and managed normally; 4. All edit/take-down operations are logged with Operator, Time and Operation Type; 5. Jobs are automatically marked as "Closed" after the deadline and cannot be edited or republished. | 3 story points | 1. Edit operations only modify the original job CSV file without generating new files; 2. Take-down status is stored in the JSON configuration file of job information; 3. Deadline automatic validation is triggered regularly by the system. | 2026-03-27 | 2026-03-31